## Slide 1: Protube – Increment PTBSYS-03-003
ProTube System
Kick-off
10/09/2026
PJM Luca Contini
MOD-KICK_OFF.1
PTBSYS-03-003 – ProTube Barcellona improvements and DMS first integration

## Slide 2: Kick-off Agenda
Agenda
Project Name and Team
01
Project Scope
02
03
04
05
Major Requirements
Product Line and P/N
06
Preliminary Effort Estimation
Timeline
MOD-KICK_OFF.1

## Slide 3: Team Members
Team Members
Team Function | Team Member name
Product Development Manager | Alberto Vidili
Project Manager | Luca Contini
TIH Software Development | Nicola Tuveri
TIH Software Development | Stefano Atzeni
TIH Software Development | Isabella Sacchi
TIH Software Development | Mirko Dessi
Firmware | Adriano Melis
TIH Software Testing | Giampinello Emanuele
TIH Software Testing | Massimo Piras
System Testing | Massimo Piras
System Testing | Giampinello Emanuele
Certification | Cristian Leotta
Compliance | Francesca Marchese
Technical Documentation | Gianni Bono
It’s recommended to conduct the kick-off meeting when the whole team can attend. Share anyway with all and also with externals to the team if necessary (e.g., commercial, service)
Other External reference | Name
Regulatory | Marta Zappella
Product Manager TTP Protube | Antimo Bianco
Cost Estimation | 
Service | 
Procurement | 
Manufacturing | 
MOD-KICK_OFF.1
Project Code for Timesheet: PTIH-PT11 - ProTube Cybersecurity Enhancements

## Slide 4: Project Scope
MOD-KICK_OFF.1

## Slide 5: Project Scope
Scope Description
Description
The release centers on building ProTube's integration with DMS for the first time, alongside a hardening of the platform's security posture, a handful of workflow refinements, and one piece of outsourced hardware support. The DMS work establishes a new, one-way data flow from ProTube to DMS: the system will expose transport missions data and transport-related notifications to DMS — both outbound only, with no corresponding capability for DMS to push data back into ProTube in this release.
Security work includes enforcing the use of an Inpeco CA server certificate during installation and introducing MTLS for all authenticated connections between PTBS and DMS, both aimed at hardening the platform's certificate and transport-layer security.
There's also a compatibility item ensuring the system works correctly with the ISAC 3P-RHL.2026.Aug.31 patch, and an outsourced hardware capability adding support for a Bluetooth printer (Sato PW2NX replacing the old PV3).
On the workflow and usability side, the goals is to improve the day-to-day lab experience: allowing postponed tubes to be scanned before patient checkout in a non-mandatory way (Enhancement ENH 02215), letting a Phlebotomist link only the rack needed for the selected group orders to the routine (Enhancement ENH 02464), and surfacing sorting category information on the checkout page without requiring confirmation (Enhancement ENH-02245). Rounding things out, the following Complaints/Bug will be solved: the Operations Manual will be updated to mitigate and fix the safety issue “Multiple tablets connected to one ProTube Master” (72154), Synchronization fails sometimes with postponed orders, App enrollment required (65507) and Missing diuresis volume on HL7 message LAB63 (69019) and finally the bug ProTube Services do not persist application logs.
Project Classification
Select the characteristics of the project ()
Project type
 NEW BUSINESS/PRODUCT
 NEW FEATURE/MODULE/CONNECTION *
 CROSS
 IMPROV & FIX
Customer Target
 INTERNAL INPECO CLIENT
 EXTERNAL SPECIFIC CLIENT
 EXTERNAL CUSTOMER PARTNER/IVD
 EXTERNAL WORLDWIDE CUSTOMERS
MOD-KICK_OFF.1
* New feature project type is flagged only in order to consider related tasks on PMC due to project complexity

## Slide 6: Additional Info about Project Scope
MOD-KICK_OFF.1

## Slide 7: Project Scope
Project Scope
EXPECTED MARKETS
This Section contains information about the expected markets for distributing the new ProTube System increment PTBSYS-03-002:
Europe
UK, USA, Australia
Saudi Arabia
Qatar
UAE
Brazil
Israel
Canada
China
The information reported in this section impacts:
Language for SW, Labels and Operation Manual Translation
The impact on Product Certification is currently under evaluation.
The impact on Product Registration is currently under evaluation.
Note: changes affecting the Project Scope implies the Project Scope document updated and a new approval process.
MOD-KICK_OFF.1

## Slide 8
Protube – PTBSYS
2025
2027
Country REGISTERED
Country NOT REGISTERED
Today
May 15
May 19
Mar 14
Aug 14
May 30
Aug 14
Q1
Q2
Q3
Q4
ITA
US
BRA (POR)
ISR
BH - QAT - SAU
Q1
Q2
Q3
2025
2026
Q4
2027
CAN (EN-FRA)
Q1
Q2
ESP
FRA
CZ
GER
Dec 31
UK - AUS
LIT
Nov 30
ROM
Mar 31
GRE
Jul 30

## Slide 9
Protube – PTBSYS
2025
2027
Today
May 15
May 19
Mar 14
Aug 14
May 30
Aug 14
Dec 31
Nov 30
Mar 31
Jul 30

## Slide 10
Protube – PTBSYS
Note:
Brazil - Registration activities will start in 2025. The quarter has not been defined yet. SW and Manuals have Portuguese as a language option.
Canada - Registration activities have not been scheduled yet. French and English will be the languages used in the SW and manuals.
QAT/BH/SAU – The registration activities date has not been scheduled yet. The SW and manuals will be in Arabic.
SW Available, Manuals to be translated - FRA
SW and Manuals, available – ESP; ITA; US
To be translated SW and Manuals – LIT; POR; GER; ISR
Manuals Available, SW to be translated - ROM
Not Registered to be Translated SW and Manuals – UK; AUS; CAN
Not Registered, SW and Manuale already in the right language – BRA; SAU; QAT; BH
Legend for translation
2024
2024
Today

## Slide 11: Project Scope
Project Scope
PROJECT CONSTRAINTS
This section contains information about the expected and known project constraints.
Below the list of possible constraints to be checked and detailed for the specific project to which this document refer to (the below listed constraints could be applicable or not and additional ones could be present for specific project development):
Sample Tubes constraints:
  Any currently ProTube supported tubes already validated and included in TUC
Barcode types constraints:
  Any Barcode symbology currently supported by ProTube
Samples Workflow on board of automation constraints:
  N/A
Lab workflow and/or special applications constraints:
  N/A
Environment constraints:
  With reference to ProTube System: as per Operations Manual 2U00000025-en-US.02, paragraph 1.10
Current Issues:
  N/A
MOD-KICK_OFF.1

## Slide 12: Project Scope
Project Scope
EXPECTED PRODUCT VOLUMES AND PRODUCT PRICE
2026 650 Units
2027 800 Units
2028 1000 Units
MOD-KICK_OFF.1

## Slide 13: Major Requirements
MOD-KICK_OFF.1

## Slide 14: Major Requirements
Major Requirements
Update transport mission events
Temperature measurements for each automatically completed mission
Temperature and duration thresholds along with the temperature values
Transport Mission starting point (origin workplace) in the mission start and mission completed events
Transport mission origin
Both the Smart Device App and the Check-in Station shall be able to show also the Transport Mission origin
The ProTube System shall send the processed patient location (origin) back to LIS through LAB-63
QMS events through App and TS
The ProTube System shall not send traceability events related to the Queue Management Service directly to DAS anymore
Support for Czech and Greek
The ProTube System shall support also Czech and Greek languages in both Smart Device App and Check-in Station
MOD-KICK_OFF.1

## Slide 15: Additional Info about Requirements
MOD-KICK_OFF.1

## Slide 16: Major Requirements
Additional Info about requirements
OPTIONAL SECTION TO INCLUDE, FOR EXAMPLE:
Benchmarking analysis
Specific goals related to target cost
Details about one of the requirements (e.g. on the sw part)
Possible targets about performances, coming from Commercial Excellence
Potential markets and consequent required translations, coming from Commercial Excellence and/or Regulatory.
Risks and Mitigation
MOD-KICK_OFF.1

## Slide 17: Product Line and P/N
MOD-KICK_OFF.1

## Slide 18: Product Line
Product Line
PTB-CLN.024 (ProTube Phlebotomy Assistant SW)
  ProTube Smart Device App PSDA 4.4.0
PTB-SRV.020 (ProTube System Server components)
  ProTube Service 6.0.0
  Queue Management Service 3.0.0
  ProTube System Installer 4.0.0
PTB-LCS.009 (ProTube Lab Check-in Station
  ProTube Lab Check-in Station 3.1.0
MOD-KICK_OFF.1
P/N coding depending on the Product Line:

## Slide 19: Preliminary Effort Estimation
MOD-KICK_OFF.1

## Slide 20: Preliminari Effort Estimation
Preliminary Effort Estimation
For this increment it is expected the following effort
Project Management: 118h
SW Development: 1574h
SW testing: 576h
System testing: 132h
Tot 2400h
MOD-KICK_OFF.1

## Slide 21: Timeline
MOD-KICK_OFF.1

## Slide 22: Timeline
Project Timeline
MOD-KICK_OFF.1
Expected timeline is reported below:
Kick-off meeting: within May ’26
Planning review: within June ’26
Execution review: within June ’26
Deployment review: within June ‘26
Start Mon 06/04/26
Finish Mon 13/07/26
13 Apr '26
27 Apr '26
11 May '26
25 May '26
08 Jun '26
22 Jun '26
06 Jul '26
Project Management Tue 07/04/26 - Tue 30/06/26
PTIH-PT11 - Traceability SW Design - Cybersecurity Development Mon 04/05/26 - Mon 15/06/26
PTIH-PT11 - Stories Refinement and TA Tue 07/04/26 - Wed 17/06/26
✔Kick Off Thu 28/05/26
Planning Thu 18/06/26
Execution Tue 30/06/26
Deployment Mon 13/07/26
Today

## Slide 23
MOD-KICK_OFF.1