## Task Guideline
Phase | Task ID | TASK Activity | OWNER | INVOLVED DEPARTMENT | OUTPUT & COMPLETION CRITERIA | MATURITY LEVEL 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | TARGET CUSTOMER: 1. Inpeco Internal Customer 2. External Specific Customer 3. External | PRODUCT TYPE Is the task specific for IVD's only? (Yes/No)
1. PLANNING PHASE | 1 | 1. ANALYSIS PROJECT OPENING | PRODUCT/PROJECT MANAGER | Product/Project Manager | 1 - 'Definition of the Project - Code for Controlling 2 - Opening the project on JIRA 3 - Opening the project on DHF sharepoint 4 - Opening the project on project management software | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 2 | 2. USER NEED COLLECTION including Performance Claims | PRODUCT MANAGER | Project Manager Product Compliance | 1 - If applicable, select "Performance Claim" in the "Impacts on" field on Jira 2 - If applicable, add project in to the "Affected Multi-project" field on Jira (Project Manager) 3 - User needs document (MOD-JUN) signed | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 3 | 3. INTENDED USE COLLECTION including product scope, customer worflow and scenarios | PRODUCT MANAGER | Project Manager Regulatory Affairs Product Compliance Quality Assurance | 1 - Fill in "Project Scope and Intended Use" field in "Planning Review" | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 4 | 4. MARKET ANALYSIS & TRANSLATION NEEDS COLLECTION including competitors, interested markets and areas, required translations based on product | PRODUCT MANAGER | Project Manager Regulatory Affairs | 1 - Fill in "Markets & Translation Needs" field in "Planning Review" | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 5 | 5. BUSINESS STRATEGY AND SALES FORECAST COLLECTION Including «How to make money» | Commercial areas (Direct, Distributor, IVD Vendor) | Project Manager Product Manager | 1 - Fill in "Volumes" field in "Planning Review" | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 6 | 6. TARGET COST COLLECTION including manufacturing, logistic, development and installation cost | PRODUCT MANAGER | Commercial areas (Direct, Distributor, IVD Vendor) Project Manager | 1 - Fill in "Target " field in "Planning Review" | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 7 | 7. TICKET(S) COLLECTION | PROJECT MANAGER | Customer Success Product Manager Manufacturing Procurement Quality Control Development Team | 1 - Fill in "Ticket" section in "Planning Review" considering: - Service Ticket(s) - Field Enhancement(s) - Manufacturing Ticket(s) (OPL and/or OBS) - IVD Vendor/Distributor Enhancement(s) - Internal Enhancement(s) - Internal Issue(s) | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 8 | 8. SUPPLY CHAIN STRATEGY PROPOSAL including Make-or-Buy | PROJECT MANAGER | Product Manager Customer Success Procurement Production Quality Manufacturing Development Team | 1 - Fill in "Meeting Minutes" field in "Planning Review" any relevant information | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 9 | 9. SUPPLY CHAIN STRATEGY DEFINITION | PROJECT MANAGER | Hardware Software Procurement Production Quality Manufacturing | 1 - Fill in "Meeting Minutes" field in "Planning Review" any relevant information | 3. Product (System) | 3. External | No
| 10 | 10. PROJECT CLASSIFICATION | PROJECT MANAGER | n.a. | 1 - Fill in "Maturity Level" field in "Planning Review" 2 - Fill in "Target Customer" field in "Planning Review" 3 - Fill in "Product Type" field in "Planning Review" | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 11 | 11. LEGAL ENGAGEMENT costraints, patent and intellectual properties collection | PROJECT MANAGER | Legal | 1 - Member invited at the Planning Review | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 12 | 12. PROJECT TEAM MEMBERS (Development Teams, Product Compliance and Product Certifications) ENGAGEMENT costraints collection | PROJECT MANAGER | Development Team Product Compliance Product Certification | 1 - Member invited at the Planning Review | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 13 | 13. REGULATORY ENGAGEMENT constraints collection | PROJECT MANAGER | Regulatory Affairs | 1 - Member invited at the Planning Review | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 14 | 14. MANUFACTURING ENGAGEMENT constraints collection | PROJECT MANAGER | Manufacturing | 1 - Member invited at the Planning Review | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 15 | 15. PRODUCTION QUALITY ENGAGEMENT constraints collection | PROJECT MANAGER | Production Quality | 1 - Member invited at the Planning Review | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 16 | 16. PRODUCT QUALITY ENGAGEMENT constraints collection | PROJECT MANAGER | Product Quality | 1 - Member invited at the Planning Review | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 17 | 17. R&D BUYER (PROCUREMENT) ENGAGEMENT costraints collection | PROJECT MANAGER | Procurement | 1 - Member invited at the Planning Review | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 18 | 18. TENDER AND ENGAGEMENT OF EXTERNAL CONSULTANS | PROCUREMENT | Project Manager Hardware Software Testing Legal | 1 - Tender issued, external consultant identified. Mail exchanges and/or meeting partecipation. NDA signed (MOD-NDA) | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 19 | 19. IVD VENDOR/THIRD PARTY FOR DEVELOPMENT AGREEMENT definition and signature | PRODUCT MANAGER | Project Manager Finance Legal | 1 - NDA and Development Agreement signed by both parties (MOD-NDA and MOD-DEA) | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 20 | 20. OFFER SHARING AND CUSTOMER PURCHASE ORDER RECEIPT | PRODUCT MANAGER | Commercial areas (Direct, Distributor, IVD Vendor) Project Manager | 1 - Purchase order receipt to start the development of activities of a specific input (e.g. development of enhancement requested by Customers) | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 21 | 21. PRELIMINARY PRODUCT CLASSIFICATION | REGULATORY AFFAIRS | Project Manager Product Certification Product Compliance Product Manager | 1 - Creation/Update of Product Qualification and Classification (MOD-IVDPQC) signed | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No
| 22 | 22. PRELIMINARY SOFTWARE SAFETY CLASSIFICATION | DEVELOPMENT TEAM | Project Manager Product Development Manager Product Compliance | 1 - 'Software Safety Classifications* (MOD-SWC) created or updated in draft, if involved software is classified as medical according IEC 62304 *Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | Yes
| 23 | 23. PERFORMANCE EVALUATION PLAN | PRODUCT COMPLIANCE | Product Manager Project Manager Regulatory Affairs | 1 - Creation/Update of Performance Evaluation Plan (MOD-PEP) signed | 3. Product (System) | 2. External Specific Customer 3. External | Yes
| 24 | 24. FEASIBILITY ESTIMATION | DEVELOPMENT TEAM | Project Manager | '1 - Fill in "Meeting Minutes" field in "Planning Review" for any relevant information (e.g. high level representation of the solution) | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 25 | 25. PROOF OF CONCEPT ASSESSMENT Focus on specific features | DEVELOPMENT TEAM | Commercial areas (Direct, Distributor, IVD Vendor) Product Manager Customer Success Project Manager Product Compliance | 1 - 'Execution of the following applicable steps: a. Time, cost and scope definition b. Material supply c. POC Design and development d. POC shared with stakeholders 2 - Fill in "Meeting Minutes" field in "Planning Review" for any relevant information | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 26 | 26. APPLICABLE TECHNICAL STANDARDS/REGULATIONS FOR SPECIFIC PRODUCTS | PROJECT MANAGER | Development Team Product Compliance Product Certification | 1 - User Stories, relevant Acceptance Criteria, link to the appropriate issue type (User Need and/or Risk) created and reported on JIRA, included System items. | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 27 | 27. EXISTING TOOL ASSESSMENT | DEVELOPMENT TEAM | Project Manager Manufacturing Customer Success | 1 - Assessment to be reported as aprt of Technical Report (HW) or fill in "Meeting Minutes" field in "Planning Review" for any relevant information | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 28 | 28. USER STORIES & ACCEPTANCE CRITERIA DEFINITION including PROJECT-SYSTEM content and including Performance Claims | PROJECT MANAGER | Development Team Product Certification Product Compliance | 1 - Team meeting. User Stories, relevant Acceptance Criteria, link to the appropriate issue type (User Need and/or Risk) created and reported on JIRA, included System items. | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 29 | 29. ESSENTIAL REQUIREMENTS CHECKLIST referred to Machinery Directive 2006/42/CE | PRODUCT CERTIFICATION | Project Manager Development Team Product Compliance | 1 - "Essential Requirement Checklist" (MOD-RESS) signed | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 30 | 30. HIGH LEVEL USER STORIES REFINEMENT | PROJECT MANAGER | Development Team Product Certification Product Compliance | 1 - 'Design Input* with User Stories (MOD-JDI) digitally signed *Deliverable complying, among others, also with standard IEC 62304 | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 31 | 31. CHANGE ORDER OPENING | PROJECT MANAGER | Development Team Product Certification Product Compliance Customer Success Commercial areas (Direct, Distributor, IVD Vendor) Quality Assurance Regulatory Affairs | 1 - Draft Change Order created and filled in 2 - Report in the "Intent of the change description" the list of the changes that needs to be evaluate for change impact 3 - Notify via email Quality Assurance and Regulatory Affairs for Change Impact Assessment (MOD-CIA) | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 32 | 32. HIGH LEVEL REGRESSION ANALYSIS | PROJECT MANAGER DEVELOPMENT TEAM (TESTER) | Project Manager Product Compliance | 1 - Draft "Regression Analysis" (MOD-REA) created and filled in (Project Manager) 2 - Define impacts on Verification and Validation on Created Regression Analysis (Tester) | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 33 | 33. CRITICALITY MATRIX for DESIGN FMEA, for critical components | DEVELOPMENT TEAM (HARDWARE) | Project Manager Development Team Product Certification Product Compliance | 1 - "Criticality Matrix" (MOD-HCM) signed 2 - "Design FMEA" (MOD-DFMEA), if needed, signed | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 34 | 34. (SAFETY/SECURITY) RISK ANALYSIS REFINEMENT | PRODUCT COMPLIANCE | Project Manager Development Team Product Certification Medical Affair | Team meeting. Safety FMEA with Risks and link to the appropriate issue type (User Need, Mitigation Method, User Stories) created and reported on JIRA, included System items. Creation / update of following documentation: 1 - 'Risk Management Plan'* (MOD-RMP1) signed 2 - 'Safety FMEA'* (MOD-FMEA1) signed 4 - 'Safety Risk Analysis'* (MOD-JRA1) signed 3 - 'Security Risk Analysis'* (MOD-JRA1) signed 5 - 'Product Lifecycle Risk Analysis'* (MOD-PLRA) signed 6 - 'Production process Risk Analysis'* (MOD-RAPP) signed *Deliverable complying, among others, also with standard IEC 62304 | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 35 | 35. FINAL PRODUCT DESCRIPTION | REGULATORY AFFAIRS | Project Manager | 1 - 'Product Description (MOD-PD) signed | 3. Product (System) | 2. External Specific Customer 3. External | No
| 36 | 36. CHANGE IMPACT ASSESSMENT | REGULATORY AFFAIRS | Project Manager Development Team Product Compliance Quality Assurance | 1 - "Change Impact Assessment" (MOD-CIA) signed | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 37 | 37. CHECK ON DEPENDENCIES FROM AND IMPACTS ON OTHER PROJECTS (INCLUDING, IF APPLICABLE, SYSTEM PROJECTS) including budget review and check with other project PM/s | PROJECT MANAGER | Project Manager | 1 - Fill in "Meeting Minutes" field in "Planning Review" any relevant information 2 -Added and review Affected Multi-project field for System Project, if applicable. | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 38 | 38. NEED CHECK FOR PRESERIE | PROJECT MANAGER | Manufacturing Production Quality | 1 - Fill in "Planning Review" the "Pre-Serie foresees?" field in case of need of Pre-Serie | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 39 | 39. SHOULD COST ANALYSIS focus on cost and value engineering team | DEVELOPMENT TEAM (HW) | Project Manager Product Manager Development Team Cost & Value Engineering | 1 - 'Cost Estimation shared and archived on SharePoint '2 - Fill in "Meeting Minutes" field in "Planning Review" any relevant information | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No
| 40 | 40. PROJECT BUDGET CONSOLIDATION Expected cost, resource, time (including man-hours) | PROJECT MANAGER | Controlling Product Manager | 1 - Fill in "Planning Review" the section related to Budget | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 41 | 41. PROJECT SCHEDULING including resources-activities mapping and costraints and sharing with involved stakeholders | PROJECT MANAGER | Development Team Product Compliance Product Certification Regulatory Affairs Manufacturing Procurement Distributor, IVD Vendor Product Manager | 1 - Fill in "Planning Review" the expected due date for all the next phases | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 42 | 42. GO-NO GO DECISION including commercial Part Number definition | PRODUCT MANAGER | Commercial areas (Direct, Distributor, IVD Vendor) Project Manager | 1 - Fill in "Project Approved" / "Go-No Go Decision" field in "Planning Review" including commercial Part Number definition | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 43 | 43. ANALYSIS PROJECT CLOSURE | PRODUCT/PROJECT MANAGER | Product/Project Manager | 1 - Closure the project on project management software | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 44 | 44. PLANNING REVIEW | PROJECT MANAGER | Product Manager Development Team Product Compliance Product Certification Regulatory Affairs Manufacturing Procurement Production Quality Product Quality Customer Success Other needed stakeholders | 1 - 'Conduction of the meeting review and "Planning Review" signed | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
2. EXECUTION | 45 | 45. DEVELOPMENT PROJECT OPENING | PROJECT MANAGER | Controlling ICT Development Team Product Compliance Product Certification All stakeholders that need to account for | 1 - 'Definition of the Project - Code for Controlling 2 - Opening the project on JIRA or report the project opened during Planning phase, if not already opened 3 - Opening the project on DHF sharepoint or report the project opened during Planning phase, if not already opened 4 - Opening the project on project management software | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 46 | 46. DETAILED REFINEMENT ACTIVITY Continuous refinement | PROJECT MANAGER | Development Team Product Certification Product Compliance | 1 - Stories are at least in "READY" status | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 47 | 47. PRELIMINARY BOM DEFINITION including any Upgrade/Retrofit Kit | DEVELOPMENT TEAM (HW) | Project Manager Product Manager Development Team | 1 - 'BOM in "PROTOTYPE" status on EPDM 2 - BOM related to Upgrade/Retrofit Kit in "PROTOTYPE" status on EPDM | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 48 | 48. MATERIAL SUPPLY FOR HW PROTOTYPE | DEVELOPMENT TEAM (HW) PROCUREMENT | Project Manager Procurement | 1 - RDA sent (HW) 2 - RA sent (HW) 3 - RA process and monitoring tool update (PROCUREMENT) 4 - RDA process and monitoring tool update (R&D HW) 5 - Task closed when all required material is received (HW) | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 49 | 49. HW PROTOTYPE DESIGN & DEVELOPMENT | DEVELOPMENT TEAM (HW) | Project Manager Development Team Product Compliance Product Certification Manufacturing | 1 - 'Physical device assembly completion 2 - 'BOM in "APPROVED FOR HW TEST" status on EPDM 3 - FORM-HWUT completed and provided to Manufacturing | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 50 | 50. SW/MCSW PROTOTYPE / DEMO DESIGN & DEVELOPMENT | DEVELOPMENT TEAM (MCSW, SW) | Project Manager Product Manager Customer Success | 1 - SW artifact on repository with dedicated PN | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 51 | 51. HW PROTOTYPE SHARING WITH PROJECT STAKEHOLDERS | DEVELOPMENT TEAM (HW) | Project Manager Commercial areas (Direct, Distributor, IVD Vendor) Product Manager Customer Success | 1 - Demo/presentation of the prototype to stakeholders '2 - Fill in "Meeting Minutes" field in "Execution Review" any relevant information | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 52 | 52. SW/MCSWPROTOTYPE / DEMO SHARING WITH PROJECT STAKEHOLDERS | DEVELOPMENT TEAM (MCSW, SW) | Project Manager Commercial areas (Direct, Distributor, IVD Vendor) Product Manager Customer Success | 1 - 'Demo/presentation of the prototype to stakeholders 2 - Fill in "Meeting Minutes" field in "Execution Review" any relevant information | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 53 | 53. LABELS Safety Labels Informative Labels Regulatory/Statutory Labels | DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS) PRODUCT CERTIFICATION | Project Manager Product Certification Regulatory Affairs | 1 - 'Design and Coding of Safety Labels (e.g. High Voltage) on EPDM (DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS)) 2 - Design and Coding of Informative Labels (e.g. Do not put weights on cover) on EPDM (DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS)) 3 - Design and codice of the regulatory/statury Labels on EPDM (PRODUCT CERTIFICATION) 4 - 'Inclusion of applicable labels in the Label BOM. (DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS)) | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 54 | 54. BOM PRESERIE REVIEW | DEVELOPMENT TEAM (HW) | Project Manager Manufacturing Procurement Development Team | 1 - 'BOM in "APPROVED FOR PRESERIE" status in EPDM | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 55 | 55. BOM PRESERIE COSTIFICATION | PROCUREMENT MANUFACTURING | Project Manager Controlling Product Manager Development Team (HW) | 1 - Fill in "Meeting Minutes" field in "Pre-Serie Launch Review", if present, or in "Execution Review" any relevant information | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 56 | 56. INPUT/OUTPUT MAPPING | DEVELOPMENT TEAM (HW) | Project Manager Development Team Product Certification | 1 - 'Input/Output Mapping (MOD-IOM) digitally signed | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 57 | 57. HW TEST | DEVELOPMENT TEAM (HW) | Project Manager Product Compliance Development Team (TESTER) | 1 - 'Verification test performed and traced on Jira tool 2 - 'Final Test Report (MOD-JTMR) filled in, only if "SYSTEM & INTEGRATION TEST has been evaluated as not required 3 - Updated Layout related to the R&D Automation System with the preserie on EPDM "APPROVED FOR PRESERIE" | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 58 | 58. TEAR DOWN | DEVELOPMENT TEAM (HW) | Project Manager Manufacturing | 1 - TEAR DOWN activities | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 59 | 59. PRE-SERIE LAUNCH REVIEW MEETING | PROJECT MANAGER | Development Team Product Compliance Product Certification Production Quality Manufacturing Procurement | 1 - 'Conduction of the meeting review and "Pre-Serie Launch Review" signed | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 60 | 60. PRESERIE DEVELOPMENT | MANUFACTURING | Project Manager Development Team Product Certification | 1 - 'Physical device assembly completion | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 61 | 61. HW DESIGN & DEVELOPMENT & INTEGRATION including specifications description and link to user stories, including device configuration development, including labels. | DEVELOPMENT TEAM (HW) | Project Manager Development Team Product Certification Product Compliance Procurement | 1 - 'Dev and/or Collection Task reported on Jira tool 2 - 'Safety Regression Analysis for safety fixes filled in on Jira tool within Root cause field 3 - 'Final Test Report (MOD-JTMR) filled in, only if "SYSTEM & INTEGRATION TEST has been evaluated as not required 4 - Task completed on Jira tool, according to department procedure and team instructions 5 - 'Internal HW check list 6 - Commercial components documents like Safety Data Sheets on EPDM 7 - Detailed Hardware Specification (MOD-DHS) digitally signed | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 62 | 62. MCSW DESIGN & DEVELOPMENT DOCUMENTATION including specifications description and link to user stories, including simulation tools development | DEVELOPMENT TEAM (MCSW) | Project Manager Development Team Product Certification Product Compliance | 1 - Design & Development Plan* (MOD-FDDP) digitally signed 2 - 'Standard Firmware Documentation* (MOD-SFD) digitally signed 3 - Other Output Documents (MOD-SDD) included Confidential Documents, Installation Procedure, if needed 4 - 'Safety Regression Analysis for safety fixes filled in on Jira tool within Root cause field *Deliverable complying, among others, also with standard IEC 62304 | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 63 | 63. SW DESIGN & DEVELOPMENT including specifications description and link to user stories, including simulation tools development | DEVELOPMENT TEAM (SW) | Project Manager Development Team Product Certification Product Compliance | 1 - 'Design & Development Plan* (MOD-SDP) digitally signed 2 - 'Software Architecture* (MOD-SDD) digitally signed 3 - 'Automation/Host LIS interface Specifications (FL-SDP) digitally signed 4 - Other Output Documents (MOD-SDD) included Confidential Documents, Analyzer Specifications Checklist, Functional Detailed Documents, Software Language Translations, Installation Procedures if needed 5 - 'Safety Regression Analysis for safety fixes filled in on Jira tool within Root cause field *Deliverable complying, among others, also with standard IEC 62304 | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 64 | 64. DESIGN SPECIFICIATION | DEVELOPMENT TEAM (HW/MCSW/SW) | Project Manager Development Team Product Certification Product Compliance | 1 - Code Review according to department procedure and team instructions 2- 'Design Specification* (MOD-DS) digitally signed *Deliverable complying, among others, also with standard IEC 62304 | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 65 | 65. FINAL SOFTWARE SAFETY CLASSIFICATION | DEVELOPMENT TEAM (MCSW/SW) | Project Manager Product Development Manager Product Compliance | 1 - 'Software Safety Classifications* (MOD-SWC) signed, if involved software is classified as medical according IEC 62304 *Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | Yes
| 66 | 66. HW/MCSW/SW TOOL (for R&D, Manufacturing, Customer Success) DESIGN & DEVELOPMENT & VALIDATION | DEVELOPMENT TEAM (HW, MCSW/SW) | Manufacturing Customer Success | 1 - Physical device assembly completion 2 - 'BOM in "APPROVED FOR HW TEST" status on EPDM 3 - 'VMP or other validation documentation completd and signed, according to PRO-00N procedure | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 67 | 67. PRELIMINARY SPARE PARTS LIST | SPARE PARTS ENGINEER | Project Manager Customer Success Development Team | 1 - Spare Parts codes in “Approved Status” on EPDM 2 - Spare Parts excel list available | 3. Product (System) | 2. External Specific Customer 3. External | No
| 68 | 68. UNIT TEST | DEVELOPMENT TEAM (MCSW/SW) | Project Manager | 1 - Task completed on Jira tool, according to department procedure and team instructions | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 69 | 69. COMPONENT TEST | DEVELOPMENT TEAM (TESTER) | Project Manager Product Compliance | 1 - 'Final Test Report* (MOD-JTMR) filled in, only if "SYSTEM & INTEGRATION TEST" has been evaluated as not required 2 - Task completed on Jira tool, according to department procedure and team instructions * Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 70 | 70. SOFTWARE EXTERNAL TRANSLATION | DEVELOPMENT TEAM (SW) PROJECT MANAGER | Project Manager Development Team (SW) Procurement | 1 - 'Label to be translated listed in a dedicated file shared with PM (Development Team (SW)) 2 - 'Translation request process to obtain label translated (Project Manager) 3 - 'Integration of translated label in software code and reported on Jira tool. Related Output document provided. (Development Team (SW)) | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 71 | 71. TRANSLATION SW TEST | DEVELOPMENT TEAM (TESTER) | Project Manager Development Team | 1 - 'Final Test Report* (MOD-JTMR) filled in, only if "SYSTEM & INTEGRATION TEST" has been evaluated as not required 2 - 'Task completed on Jira tool, according to department procedure and team instructions * Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 72 | 72. SW MEDIA | DEVELOPMENT TEAM (HW/SW/MCSW) | Project Manager Development Team (TESTER) Product Compliance | 1 - Check that the content of SW Media has been appropriately loaded (Activity DONE - SW Engineer) 2 - Check that the content of SW Media has been appropriately loaded (Activity DONE - MCSW Engineer) 3 - Check that the content of SW Media has been appropriately loaded (Activity DONE - HW Electrical Engineer) 4 - SW Artifact with its own P/N has been loaded on repository per Software Design & Development Plan document. | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 73 | 73. SYSTEM & INTEGRATION TEST | DEVELOPMENT TEAM (TESTER) | Project Manager Product Compliance Development Team Biotech | 1 - 'Final Test Report* (MOD-JTMR) filled in and digitally signed 2 - Task completed on Jira tool, according to department procedure and team instructions *Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 74 | 74. INSTALLATION CHECKLIST | DEVELOPMENT TEAM | Project Manager Product Compliance Documentation | 1 - Installation checklist (MOD-CHL) filled in by all project team members and approved on SharePoint | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 75 | 75. OPERATIONS MANUAL DRAFT | DEVELOPMENT TEAM (HW) | Project Manager Development Team (TESTER) Product Compliance | 1 - Operations Manual draft | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No
| 76 | 76. SERVICE MANUAL DRAFT | DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS) | Project Manager Development Team (TESTER) Product Compliance Customer Success | 1 - Service Manual draft | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 77 | 77. PRODUCTION INSTRUCTIONS DRAFT | DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS) | Project Manager Development Team (TESTER) Product Compliance Customer Success | 1 - Production Instructions in draft | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 78 | 78. BUG REPORT/REVIEW AND ASSESSMENT ON EVENTUAL REWORK including items from Preserie | DEVELOPMENT TEAM (TESTER) | Project Manager Product Compliance Regulatory Affairs Development Team Manufacturing Customer Success | 1 - 'Technical issue list document* (MOD-JTIL) signed 2 - ' Preserie Issue List document loaded on SharePoint 3 - 'Evaluation if additional development/testing activities are required to fix the open bugs. Review the previous tasks status completion and potentially replan them with the team. *Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 79 | 79. CONSISTENCY CHECK BETWEEN "PLANNING" PHASE AND "EXECUTION" PHASE | PROJECT MANAGER | n.a. | 1 - Include in the "Execution Review" sheet under "Deliverable Check - update from previous Reviews" the list of updated deliverables fromn previous phases 2- Fill in "Meeting Minutes" field in "Execution Review" any relevant information | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 80 | 80. BOM FINAL DEFINITION | DEVELOPMENT TEAM (HW) | Project Manager Product Manager Development Team | 1 - 'BOM in "APPROVED" status in EPDM | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 81 | 81. PRODUCT CERTIFICATION SESSION | PRODUCT CERTIFICATION | Certification Body (External) | 1 - Involved Tests (e.g. safety tests, EMC tests) successfully completed | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No
| 82 | 82. DESIGN & DEVELOPMENT | PROJECT MANAGER | Development Team Product Certification Product Compliance | 1 - all Stories are in DONE 2 - Bugs related to Stories not met have been opened | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 83 | 83. COMPATIBILITY ASSESSMENT | DEVELOPMENT TEAM | Project Manager Product Compliance Customer Success | 1 - 'Compatibility Matrix (HW-FW-SW driver) document, as filled and reported on SharePoint 2 - 'Driver-Core Compatibility (SW driver - SW core) document digitally signed 3 - 'Software Core Compatibility document digitally signed | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 84 | 84. EXECUTION REVIEW MEETING | PROJECT MANAGER | Product Manager Development Team Product Compliance Product Certification Regulatory Affairs Manufacturing Production Quality Procurement Customer Success | 1 - 'Conduction of the meeting review and "Execution Review" digitally signed | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
3. DEPLOYMENT | 85 | 85. PRODUCT COST FINAL DEFINITION | CONTROLLING | Commercial areas (Direct, Distributor, IVD Vendor) Product Manager Development Team (HW) | 1 - Fill the Product BOM cost information (Dynamics 365) 2- Fill in "Meeting Minutes" field in "Deployment Review" any relevant information | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 86 | 86. TRAINING TO INPECO TECHNICAL / NON-TECHNICAL STAFF | PROJECT TEAM | Project Team Customer Success Product Manager Manufacturing Commercial areas (Direct, Distributor, IVD Vendor) | 1 - Planning the training content and coordinate department availability. (Project Manager) 2 - Prepare, conduct and register attendees on Inpeco Academy for the meeting (Development Team) 3 - Upload training session and questionnaires on Inpeco Academy 4 - Release Training Agenda (MOD-RTA) digitally signed | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 87 | 87. OPERATIONS MANUALS FINAL | DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS) | Project Manager | 1 - Operations Manual approved and loaded on internal Inpeco repository (Sharepoint) - internal use only | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No
| 88 | 88. SERVICE MANUALS FINAL | DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS) | Project Manager | 1 - Installation Checklist included in the Service Manual 2- Service Manual approved and loaded on internal Inpeco repository (Sharepoint) - internal use only | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 89 | 89. PRODUCTION INSTRUCTIONS FINAL | DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS) | Project Manager | 1 - Testing Instructions loaded on repository (Sharepoint) 2 - Assembly Instructions loaded on repository (Sharepoint) 3 - Cabling Instructions loaded on repository (Sharepoint) 4 - Labeling Instructions loaded on repository (Sharepoint) 5 - Packaging Instructions loaded on repository (Sharepoint) | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 90 | 90. OPERATIONS MANUAL TRANSLATION | DEVELOPMENT TEAM (TECHNICAL DOCUMENTATION & MANUALS) | Project Manager | 1 -Translated Operations manual loaded on internal Inpeco repository (Sharepoint) - internal use only | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No
| 91 | 91. FINAL RISK EVALUATION | PRODUCT COMPLIANCE | Project Manager Project Team Members Medical Affairs | 1 - Final Risk Evaluation document (MOD-FRE) digitally signed. | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 92 | 92. TECHNICAL FILE UPDATE | PRODUCT COMPLIANCE | Project Manager | 1 - Reference to Deployment Review included in TDF Draft, for medical device only | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 93 | 93. OTHER APPLICABLE TECHNICAL FILE UPDATE | PRODUCT CERTIFICATION | Project Manager Product Compliance Product Manager | 1 - Applicable Technical Files updated (e.g. Reach/Rohs) | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 94 | 94. DESIGN AND DEVELOPMENT VALIDATION TEST | DEVELOPMENT TEAM (TESTER) | Project Manager Customer Success Product Manager | 1 - Validation test protocol executed and approved 2 - Validation Test Report (MOD-JTMR) digitally signed* *Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No
| 95 | 95. REVIEW OPEN BUGS | DEVELOPMENT TEAM | Project Manager Product Compliance Regulatory Affairs Medical Affairs | 1 - Assessment for issues safety, with direct impact on User Needs, with direct impact on Risks to be defined and included in "Deployment Review" 2 - Check that there are no Bug on Jira in "To Do" or "Analysis" | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 96 | 96. CONSISTENCY CHECK BETWEEN "PLANNING", "EXECUTION" AND "DEPLOYMENT" PHASE | PROJECT MANAGER | n.a. | 1 - Include in the "Deployment Review" sheet under "Deliverable Check - update from previous Reviews" the list of updated deliverables fromn previous phases 2- Fill in "Meeting Minutes" field in "Deployment Review" any relevant information | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 97 | 97. PERFORMANCE CLAIM LIST CREATION/UPDATE | PRODUCT MANAGER | Project Manager | 1 Creation/Update of Performance Claim List document | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 98 | 98. DEVICE MASTER RECORD UPDATE | PRODUCTION QUALITY | Project Manager | 1 - Device master Record approved and loaded on repository | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 99 | 99. PERFORMANCE EVALUATION REPORT | PRODUCT COMPLIANCE | Product Manager Project Manager Regulatory Affairs Medical Affairs | 1 - 'Performance Evaluation Report* (MOD-PERR) signed | 3. Product (System) | 2. External Specific Customer 3. External | Yes
| 100 | 100. RISK MANAGEMENT SUMMARY | PRODUCT COMPLIANCE | n.a. | 1 - Evaluate the need to updated the Risk Management Summary* (MOD-RMS). Document shall be reviewed at least once a year according to Risk Management Plan | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 101 | 101. POST MARKET PERFORMANCE FOLLOW UP PLAN | REGULATORY AFFAIRS | Product Manager Medical Affairs | 1 - 'Post Market Performance Follow Up Plan* (MOD-PMPFP) signed | 3. Product (System) | 2. External Specific Customer 3. External | Yes
| 102 | 102. POST MARKET SURVEILLANCE PLAN | REGULATORY AFFAIRS | Product Manager Customer Success Medical Affairs | 1 - 'Post Market Surveillance Plan* (MOD-PMSP) signed | 3. Product (System) | 2. External Specific Customer 3. External | Yes
| 103 | 103. GENERAL SAFETY AND PERFORMANCE | PRODUCT COMPLIANCE | Product Certification Regulatory Affairs | 1 - "General Safety and Performance Requirement" (MOD-GSPR) | 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | Yes
| 104 | 104. PRODUCT CERTIFICATE/REPORT | PRODUCT CERTIFICATION | Project Manager | 1 - Quality marks achievement (e.g. cUs, Inmetro) 2 - Certifications reports approved and loaded on repository | 3. Product (System) | 2. External Specific Customer 3. External | No
| 105 | 105. CHANGE ORDER COMPLETION | PROJECT TEAM REGULATORY AFFAIRS PRODUCT CERTIFICATION | Project Manager | 83.1 - 'Draft Change Order filled in by all the involved team members and departments 2 - Change Order* Approved 3 - Change Order Package completion * Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 106 | 106. REGRESSION ANALYSIS AND RELEASE REPORT COMPLETION | PROJECT MANAGER | Project Team | 1 - 'Draft Regression Analysis (MOD-REA) filled in. 2 - Draft Release Report (MOD-JRR) filled in. 3 - After other departments completion, Regression Analysis* (MOD-REA) digitally signed. 4 - Release Report (MOD-JRR) digitally signed. * Deliverable complying, among others, also with standard IEC 62304 | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 107 | 107. ANALYZER COMPATIBILITY | PRODUCT COMPLIANCE | Project Team | 1 - Analyzer Compatibility (MOD-AICOMP) updated | 3. Product (System) | 2. External Specific Customer 3. External | Yes
| 108 | 108. DEPLOYMENT REVIEW MEETING | PROJECT MANAGER | Commercial areas (Direct, Distributor, IVD Vendor) Product Manager Development Team Product Compliance Product Certification Regulatory Affairs Manufacturing Procurement Controlling Customer Success | 1 - 'Conduction of the meeting and "Deployment Review" digitally signed | 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 109 | 109. EU DECLARATION OF CONFORMITY | QUALITY ASSURANCE | Project Manager Regulatory Affairs Product Compliance | 1. Update to EU Declaration of Conformities | 3. Product (System) | 2. External Specific Customer 3. External | No
| 110 | 110. OTHER APPLICABLE DECLARATIONS | PRODUCT CERTIFICATION | Project Manager Quality Assurance | 1 - Update to Declaration of Conformities (e.g. Reach) | 3. Product (System) | 2. External Specific Customer 3. External | No
| 111 | 111. TECHNICAL DATA SHEET CREATION/UPDATE | PRODUCT MANAGER | Project Manager | 1 - Creation/Update of Technical Data Sheet | 3. Product (System) | 2. External Specific Customer 3. External | No
| 112 | 112. PRODUCT REGISTRATION | REGULATORY AFFAIRS | Project Manager | 1- 'Clearance obtained | 3. Product (System) | 2. External Specific Customer 3. External | No
| 113 | 113. PROJECT OUTPUT RELEASE TO DISTRIBUTOR based on Distributor agreements and considering packages/docs | PRODUCT MANAGER | Commercial areas (Direct, Distributor, IVD Vendor) Distributor Innovation & Customer Solution | 1 - Sharing of Project Package (SW/Independent release) 2 - Sharing of technical documentation | 3. Product (System) | 2. External Specific Customer 3. External | No
| 114 | 114. TRAINING TO DISTRIBUTOR/CUSTOMER TECHNICAL / NON-TECHNICAL STAFF | PRODUCT MANAGER/ CUSTOMER SUCCESS | Project Manager Distributor | 1 - Training planned 2- Once conducted, training records and questionnaires filled in | 3. Product (System) | 2. External Specific Customer 3. External | No
| 115 | 115. CUT-IN DEFINITION | MANUFACTURING | Project Manager Product Manager | 1 - Cut-in defined, agreed and shared 2- Fill in "CUT IN identified" field in "Release to Market Review" | 3. Product (System) | 2. External Specific Customer 3. External | No
| 116 | 116. TECHNICAL SERVICE BULLETING/INSTRUCTION FOR SERVICE (TSB/ISA) | CUSTOMER SUCCESS | Project Manager Product Manager | 1 - TSB / ISA approved and loaded on Service Portal | 3. Product (System) | 2. External Specific Customer 3. External | No
| 117 | 117. DOCUMENTS FOR MARKET RELEASE | PRODUCT MANAGER | Commercial areas (Direct, Distributor, IVD Vendor) Marketing Project Manager Regulatory Affairs | 1 - Product Information, other documents… | 3. Product (System) | 2. External Specific Customer 3. External | No
| 118 | 118. RELEASE NOTICE TO INPECO | PROJECT MANAGER | Product Manager Development Team Product Compliance Product Certification Regulatory Affairs Manufacturing Procurement | 1 - Email to Inpeco stakeholders (e.g. DL-ReleaseNotice@inpeco.com) to inform Inpeco of the release | 3. Product (System) | 2. External Specific Customer 3. External | No
| 119 | 119. RELEASE NOTICE TO MARKET | PRODUCT MANAGER | Project Manager Distributor | 1 - 'Email/other communication means to inform other stakeholder of the release | 3. Product (System) | 2. External Specific Customer 3. External | No
| 120 | 120. DEVELOPMENT PROJECT CLOSURE | PROJECT MANAGER | Product Manager | 1 - Closure the project on project management software | 1. Idea / Proof of Concept 2. Prototype / Demo 3. Product (System) | 1. Inpeco Internal Customer 2. External Specific Customer 3. External | No
| 121 | 121. RELEASE TO MARKET REVIEW MEETING | PROJECT MANAGER | Commercial areas (Direct, Distributor, IVD Vendor) Product Manager Product Compliance Product Certification Regulatory Affairs Manufacturing Procurement Customer Success | 1 - 'Conduction of the meeting and "Release to Market Review" digitally signed | 2. Prototype / Demo 3. Product (System) | 2. External Specific Customer 3. External | No

## Kick-off Review (hidden)
Kick-off Review Meeting
Date |  |  | YYYY/MM/DD
Meeting Attendees and Roles
Name & Surname |  |  |  | Company Roles
In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx" |  |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Report the name and surname of the Independent Reviewer. (Contact the Head of Lifecycle unit or Q&R for the independent reviewer person) |  |  |  | Company Role - Independent Reviewer
Project Classification
Project Category
Maturity Level
Target Customer
Competence Area
Increment #
Project Team Members
Project Manager |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
SW Engineer |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
MCSW Engineer |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
HW Engineer |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Compliance Specialist |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Tester |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
…. |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Project Scope & Intended use
Report here the Project Scope and the defined Intended use
Deliverable Check
Name |  |  |  |  | File
Design Input - User Needs [Document (based on MOD-JUN) digitally signed] |  |  |  |  | Provide document code and version (eg. FL-UN.1)
Ticket Description (Tickets may belong to Service Tickets, Field/Internal/Third-Parties Enhancements, Internal Issues, Manufacturing Tickets)
Reference ID | Input List | Description |  |  | Input Owner | Notes/Updates
add more rows if needed
Product Description
Expected Product Performances |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
LAS Interface |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
HW Interface |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
LAS Communication Protocol |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
LIS Communication Protocol |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Product Constraints |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Sample Tubes |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Workflow Constraints |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Current Issues |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Application Constraints |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Business Expectations
Product Delivery Date |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Volumes |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Target Cost |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Markets |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
New/Update to available Language |  |  | List here the new languages or the ones that needs to be updated
Preliminary Project Budget
Hours | Total XX Hours |  | Total XX Hours
Materials | XXXX € |  | XXXX €
Meeting Minutes
In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx" For the Action Item refer to "Action Items" sheet.
Pre-Serie foresees? |  |  | YES/NO
GO-NO GO Decision |  |  | GO/NO-GO
Project Approved (i.e. could we move to the Planning phase)? |  |  | YES/NO
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Necessario coinvolgere anche Produzione e Supplier Quality Reply: Possiamo evitare il PPTX almeno per il team e le informazioni che vanno qui per forza?
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Da tenere?
Note on A26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Secondo me è importante riportare qui e non nel power point l’informazione essendo che questa sarà la review approvata
Note on A29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vogliamo lasciare citati I nomi dei template?
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Propongo di spostarla qui invece che avere un foglio dedicato o no? Reply: Nel caso reintrodurre le righe di prima
Note on A50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cosa ne pensate? Alla fine serve anche per capire potenziale budget necessario
Note on A55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Secondo me qui è importante riportare l’informazione essendo che questa sarà la review approvata

## Attachment A - Tickets (hidden)
Tickets
Reference ID | Input List | Description | Input Owner | Notes/Updates

## Cover
PLANNING/EXECUTION REVIEW/DEPLOYMENT/RELEASE TO MARKET REVIEW PROJECT NAME - INCREMENT #
This document has been reviewed and approved for release by the persons below. Approval by signature as indicated.
| Project Team Function | Name | Signature and Date
Project Manager
Product Compliance Engineer
Independent Reviewer - add the job title
Product Manager (only for Planning/Deployment/Release to Market Review)
Production Quality Manager (only for Pre-Serie Launch Review)
Product Development Manager (only for Planning/Deployment/Release to Market Review)
Head of Development (for AP projects only) (only for Planning/ Deployment/Release to Market Review)
Head of SW & Integrated System (for TTP SW projects only) (only for Planning/ Deployment/Release to Market Review)
Head of Mechatronics (for TTP Mechatronics projects only) (only for Planning/ Deployment/Release to Market Review)
Medical Affairs (only for Deployment Review, based on acceptance criteria)
Third Party (only for Planning/ Deployment Review and Release to Market Review, in case of Third Party Release)
Note: the complete document includes the following worksheets: Cover, Planning Review, Execution Review, Deployment Review, Release to Martket Review, Action Items.
AUTHOR & REVISION HISTORY
Version | Author | Change Description
Version | Name | Describe reason of change. Differentiate changes if there is more the one reason.

## Planning Review
Planning Review Meeting
Date |  |  | YYYY/MM/DD
Meeting Attendees and Roles
Name & Surname |  |  |  | Company Roles
Report the name and surname of the Independent Reviewer. (Contact the Head of Lifecycle unit or Q&R for the independent reviewer person) |  |  |  | Company Role - Independent Reviewer
Project Classification
Maturity Level
Target Customer
Product Type
Increment #
Project Team Members
Project Manager |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
SW Engineer |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
MCSW Engineer |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
HW Engineer |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Product Compliance Specialist |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Tester |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Additional Job Title |  |  | In case Kick-off is performed by means of a powerpoint, report "Refer to "powerpoint title".pptx"
Product Line
In case of release as part of Product, report the Product Line otherwise report N/A FlexLab STD, HT, X, a3600, Aptio by Inpeco (Aptio 2), Aptio by Siemens (Aptio 1) ProTube FlexPath Trace, Blox, Store, Move Product Component Life Sciences products
Project Scope & Intended Use
Report here the Project Scope and the defined Intended use
Markets & Translation Needs
Report here the expected Markets and the new languages.
Volumes
Report here the expected Volumes for Product
Target Cost
Report here the expected Target Cost for Product, including manufacturing, logistic, development and installation cost
Tickets Description (considering: Service Tickets, Field Enhancements, Manufacturing Tickets (OPL and/or OBS), IVD Vendor/Distributor Enhancements, Internal Enhancements, Internal Issues)
Reference ID | Input List | Description |  |  | Input Owner | Notes/Updates
add more rows if needed
Deliverable Check
Name |  |  |  | File |  | Note
User Needs [Document signed] |  |  |  | Provide document code and version (eg. FL-UN.1) |  | Report here any reason of not applicability or not updated
Product Qualification and Classification [Document signed] |  |  |  | Provide document code and version (eg. TLA-IVDPQC.1) |  | Report here any reason of not applicability or not updated
Product Description [Document signed] |  |  |  | Provide document code and version (eg. FL-PD.1) |  | Report here any reason of not applicability or not updated
Change Order draft [Intent of Change fixed] |  |  |  | Provide CO number (e.g. CO2026-0001) |  | Report here any reason of not applicability or not updated
Change Impact Assessment [Document signed] |  |  |  | Provide document code and version |  | Report here if it a Major or Minor Change Report here any reason of not applicability or not updated
Performance Evaluation Plan [Document signed] |  |  |  | Provide document code and version (e.g. FL-PEP.1) |  | Report here any reason of not applicability or not updated
Essential Requirement Checklist [Document signed] |  |  |  | Provide document code and version (e.g. FL-RESS-XYZ.1) |  | Report here any reason of not applicability or not updated
Design Input [Document signed] |  |  |  | Provide document code and version (e.g. FL-DI-XYZ.1) |  | Report here any reason of not applicability or not updated
Risk Management Plan [Document signed] |  |  |  | Provide document code and version (e.g. FL-RMP.1) |  | Report here any reason of not applicability or not updated
Safety FMEA [Document signed] |  |  |  | Provide document code and version (e.g. FL-FMEA-XYZ.1) |  | Report here any reason of not applicability or not updated
Safety Risk Analysis [Document signed] |  |  |  | Provide document code and version (e.g. FL-RA-XYZ.1) |  | Report here any reason of not applicability or not updated
Security Risk Analysis [Document signed] |  |  |  | Provide document code and version (e.g. SECRA-XYZ.1) |  | Report here any reason of not applicability or not updated
Product Lifecycle Risk Analysis [Document signed] |  |  |  | Provide document code and version (e.g. PLRA.1) |  | Report here any reason of not applicability or not updated
Production Process Risk Analysis [Document signed] |  |  |  | Provide document code and version (e.g. RAPP.1) |  | Report here any reason of not applicability or not updated
Criticality Matrix [Document signed] |  |  |  | Provide document code and version (e.g. FL-HCM-XYZ.1) |  | Report here any reason of not applicability or not updated
Design FMEA [Document signed] |  |  |  | Provide document code and version (e.g. FL-DFMEA-XYZ.1) |  | Report here any reason of not applicability or not updated
any other additional deliverable [Document signed] |  |  |  | Provide document code and version |  | Report here any reason of not applicability or not updated
Timeline
Expected Pre-Serie Launch Review |  |  |  | YYYY/MM/DD, if foresees
Expected Execution Review |  |  |  | YYYY/MM/DD
Expected Deployment Review |  |  |  | YYYY/MM/DD
Expected Release to Market Review |  |  |  | YYYY/MM/DD
Budget
Reference Document |  |  |  | Provide document code and version (e.g. FL-BDG-XYZ)
Man-Hours |  |  |  | XXX Man-Hours Remove in case of sharing with Third-Parties
Materials |  |  |  | XXXX €
Acceptance Criteria
Are Design Input considered adequate? |  |  |  | YES/NO
Are Project Constraints approved (i.e. Design Input-Scope-Plan-Cost. Could we move to the Execution phase)? |  |  |  | YES/NO
If one or more Acceptance Criteria answer/s is/are "NO", plan related actions to be mandatory performed within a new Planning Review or the Execution Review and provide a justification for actions (not mandatory) that will not be completed within the Deployment Review. Report all evaluations in the Meeting Minutes section.
Product Description
Expected Product Performances |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
LAS Interface |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
HW Interface |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
LAS Communication Protocol |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
LIS Communication Protocol |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
Product Constraints |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
Sample Tubes - Qualification Needs |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
Workflow Constraints |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
Current Issues |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
Application Constraints |  |  | Report here the needed information or report "Refer to "powerpoint title".pptx"
Meeting Minutes
Report here the meeting minutes of the conducted review. For the Action Item, refer to "Action Items" sheet. Any additional notes/comments.
Pre-Serie foresees? |  |  | YES/NO
Controlled Launch foresees? |  |  | YES/NO
GO-NO GO Decision |  |  | GO/NO-GO
Project Approved (i.e. could we move to the Execution phase)? |  |  | YES/NO If YES report here Commercial Part Number definition

## Pre-Serie Launch Review
Pre-Serie Launch Review Meeting
Date | YYYY/MM/DD
Meeting Attendees and Roles
Name & Surname |  | Company Roles
Production Quality Manager
Production Manager
Report the name and surname of the Independent Reviewer. (Contact the Head of Lifecycle unit or Q&R for the independent reviewer person) |  | Company Role - Independent Reviewer
Deliverable Check
Name |  | File |  | Note
Pre-Serie BOM Approved [all the following points shall be in "Approved for Pre-Serie" status in EPDM: • Pre-serie released Assembly codes • Pre-serie released Mechanical bill of material • Pre-serie released Electrical bill of material • Pre-serie released Drawings (2-D and 3-D) of assembly and particulars (gates, tags and manifolds with grafoplast) that include indications for mounting and notes about the weight • Pre-serie released Drawings with wiring diagrams • Pre-serie released Product labels bill of material • Drawings with pneumatic diagrams • Configuration files of third party devices • Custom indications for track cover and track panels • Pre-serie dedicated upper cover • Pre-serie dedicated lower panel • Installation Technical Specification • Layout CAD Assembly Drawing • Packaging] |  | Provide BOM code and version |  | Report here any reason of not applicability or not updated
Input/Output Mapping [Document signed] |  | Provide document code and version (eg. FL-IOM-XXX.1) |  | Report here any reason of not applicability or not updated
any other additional deliverable [Document signed] |  | Provide document code and version | Report here any reason of not applicability or not updated
Acceptance Criteria
Have all expected and planned deliverables been successfully completed and accepted for Pre-Serie production? |  |  |  |  | YES/NO
Have the HW test been completed and documented for starting the Pre-Serie production? |  |  |  |  | YES/NO
Update the "Action Item Status" in the Action Item Sheet: Are all the action items closed? (if any) |  |  |  |  | YES/NO
Can the Pre-Serie production be launched? |  |  |  |  | YES/NO
If one or more Acceptance Criteria answer/s is/are "NO", plan related actions to be mandatory performed within a new Pre-Serie Launch Review or the Execution Review. Report all evaluations in the Meeting Minutes section.
Meeting Minutes
Report here the meeting minutes of the conducted review. For the Action Item, refer to "Action Items" sheet. Any additional notes/comments.

## Execution Review
Execution Review Meeting
Date | YYYY/MM/DD
Meeting Attendees and Roles
Name & Surname |  | Company Roles
Production Manager - in case of Pre-Serie Launch Review had been conducted
Report the name and surname of the Independent Reviewer. (Contact the Head of Lifecycle unit or Q&R for the independent reviewer person) |  | Company Role - Independent Reviewer
Deliverable Check
Name |  | File | Note
Input/Output Mapping [Document signed] |  | Provide document code and version (eg. FL-IOM-XXX.1) | Report here any reason of not applicability or not updated
Detailed Hardware Specification [Document signed] |  | Provide document code and version (eg. FL-DHS-XXX.1) | Report here any reason of not applicability or not updated
Module Control Software Design & Development Plan [Document signed] |  | Provide document code and version (eg. FL-FDDP-XXX.1) | Report here any reason of not applicability or not updated
Standard Firmware Documentation [Document signed] |  | Provide document code and version (eg. FL-SFD-XXX.1) | Report here any reason of not applicability or not updated
Software Design & Development Plan [Document signed] |  | Provide document code and version (eg. FL-SDP-XXX.1) | Report here any reason of not applicability or not updated
Software Architecture [Document signed] |  | Provide document code and version (eg. FL-SA.1) | Report here any reason of not applicability or not updated
Design Specification [Document signed] |  | Provide document code and version (eg. FL-DS-XXX.1) | Report here any reason of not applicability or not updated
Final Test Report [Document signed] |  | Provide document code and version (eg. FL-FTR-XXX.1) | Report here any reason of not applicability or not updated
Technical issue list [Document signed] |  | Provide document code and version (eg. FL-TIL-XXX.1) | Report here any reason of not applicability or not updated
Installation checklist [Document filled in and loaded on SharePoint] |  | Provide document code and version (eg. FL-CHL-XXX.1) | Report here any reason of not applicability or not updated
Software Safety Classifications [Document signed] |  | Provide document code and version (eg. FL-SWC-XXX.1) | Report here any reason of not applicability or not updated
Compatibility Matrix (HW-MCSW-SW driver) [Document signed] |  | Provide document code and version (eg. FL-CM-XXX.1) | Report here any reason of not applicability or not updated
Driver-Core Compatibility (SW driver - SW core) [Document signed] |  | Provide document code and version (eg. FL-DCC.1) | Report here any reason of not applicability or not updated
Software Core Compatibility [Document signed] |  | Provide document code and version (eg. FL-SCC.1) | Report here any reason of not applicability or not updated
Automation/Host LIS Interface Specifications [Document signed] |  | Provide document code and version (eg. FL-INT.1) | Report here any reason of not applicability or not updated
HW/MCSW/SW Tool Validation [Document signed] |  | Provide document code and version (eg. VMP-XXX.1) | Report here any reason of not applicability or not updated
Other Software Output Documents [Document signed] |  | Provide document code and version (eg. FL-SD-XXX.1) | Report here any reason of not applicability or not updated
any other additional deliverable [Document signed] |  | Provide document code and version | Report here any reason of not applicability or not updated
Deliverable Check - update from previous Reviews
Name |  | File | Note
Report the deliverable updated from previous Review |  | Provide document code and version | Report here the reason of the change from previous version
add more rows if needed |  | Provide document code and version | Report here the reason of the change from previous version
Acceptance Criteria
Have all expected and planned deliverables been successfully completed? |  |  |  | YES/NO
Conclusion of the Pre-Serie Design Transfer: are the design and development outputs verified as suitable for manufacturing? |  |  |  | YES/NO
Are all bugs with HIGH severity due to Safety YES Closed? (if any) |  |  |  | YES/NO
Are all bugs with HIGH severity due to impact on basic feature that gets product unusable closed? (if any) |  |  |  | YES/NO
Are all bugs with HIGH severity due to impact on Performance Claim closed? (if any) |  |  |  | YES/NO
Are all bugs with HIGH severity due to safety risk with impact on Mitigation Method closed? (if any) |  |  |  | YES/NO
Are all bugs with HIGH severity due to security risk defined as Uncontrolled closed? (if any) |  |  |  | YES/NO
Are all bugs with HIGH severity due to vulnerability severity (refer to CVSS v.3 Score – Inpeco use) as Critical closed? (if any)" |  |  |  | YES/NO
Are all bugs with HIGH severity due to security risk with impact on loss of confidentiality closed? (if any) |  |  |  | YES/NO
Update the "Action Item Status" in the Action Item Sheet: Are all the action items closed? (if any) |  |  |  | YES/NO
Execution Review Passed? |  |  |  | YES/NO
If one or more Acceptance Criteria answer/s is/are "NO", plan related actions to be mandatory performed within a new Execution Review or the Deployment Review and provide a justification for actions (not mandatory) that will not be completed within the Deployment Review. Report all evaluations in the Meeting Minutes section.
Meeting Minutes
Report here the meeting minutes of the conducted review. For the Action Item, refer to "Action Items" sheet. Any additional notes/comments.

## Deployment Review
Deployment Review Meeting
Date | YYYY/MM/DD
Meeting Attendees and Roles
Name & Surname |  | Company Roles
Report the name and surname of the Independent Reviewer. (Contact the Head of Lifecycle unit or Q&R for the independent reviewer person) |  | Company Role - Independent Reviewer
Deliverable Check
Name |  | File | Note
BOM Approved [BOM, including Labels, shall be in "Approved" status in EPDM] |  | Provide BOM code and version | Report here any reason of not applicability or not updated
MCSW & SW Package |  | Provide PN package code and version | Report here any reason of not applicability or not updated
Operations Manual [Document Approved, but not shared] |  | Provide document code and version (e.g. 3UXXXXXX.-en-US.01 and FL-OMA-XXX.1) | Report here any reason of not applicability or not updated
Translated Operations Manuals [Document Approved, but not shared] |  | Provide all the document code and version (e.g. 3UXXXXXX.-da-DK.01) | Report here any reason of not applicability or not updated
Service Manual [Document Approved, but not shared] |  | Provide document code and version (e.g. 3MXXXXXX.-en-US.01 and FL-ASM-XXX.1) | Report here any reason of not applicability or not updated
Production Instructions [Documents Approved and shared to Production] |  | Provide all the document code and version (e.g. FLEXISTXXX-XX.1 and FL-ALI-XXX.1) | Report here any reason of not applicability or not updated
Final Risk Evaluation [Document signed] |  | Provide document code and version (e.g. FL-FRE.1) | Report here any reason of not applicability or not updated
Validation Test Report [Document signed] |  | Provide document code and version (e.g. FL-VAR-XXX.1) | Report here any reason of not applicability or not updated
Performance Claim List [Document updated] |  | Provide document code and version (e.g. FL-PCL-XXX.1) | Report here any reason of not applicability or not updated
Technical Files [Document updated] |  | Provide document code and version (e.g. FL-TDF.1) | Report here any reason of not applicability or not updated
Other Technical Files [Document updated] |  | Provide documents codes and versions for applicable technical files (e.g. Reach/Rohs) | Report here any reason of not applicability or not updated
Change Order [Document signed] |  | Provide CO number (e.g. CO2026-0001) | Report here any reason of not applicability or not updated. Is it for a Controlled Launch?
Regression Analysis [Document signed] |  | Provide document code and version (e.g. FL-REA-XXX.1) | Report here any reason of not applicability or not updated
Release Report [Document signed] |  | Provide document code and version (e.g. FL-RR-XXX.1) | Report here any reason of not applicability or not updated
Release Training Agenda (Inpeco Internal) [Document signed] |  | Provide document code and version (e.g. FL-RTA-XXX.1) | Report here any reason of not applicability or not updated
Performance Evaluation Report [Document signed] |  | Provide document code and version (e.g. FL-PER-XXX.1) | Report here any reason of not applicability or not updated
Post Market Performance Follow Up Plan [Document signed] |  | Provide document code and version (e.g. FL-PMPFP-XXX.1) | Report here any reason of not applicability or not updated
Post Market Surveillance Plan [Document signed] |  | Provide document code and version (e.g. FL-PMSP.1) | Report here any reason of not applicability or not updated
General Safety and Performance Requirement [Document signed] |  | Provide document code and version (e.g. FL-GSPR.1) | Report here any reason of not applicability or not updated
Device Master Record [Document signed] |  | Provide document code and version (e.g. FL-DMRI.1) | Report here any reason of not applicability or not updated
Analyzer Compatibility [Document updated] |  | Provide document code and version | Report here any reason of not applicability or not updated
Product Certificate or Reports [Document uploaded] |  | Provide document code and version of the certificate/report (e.g. for EMC) | Report here any reason of not applicability or not updated
any other additional deliverable [Document signed] |  | Provide document code and version | Report here any reason of not applicability or not updated
Deliverable Check - update from previous Reviews
Name |  | File | Note
Report the deliverable updated from previous Review |  | Provide document code and version | Report here the reason of the change from previous version
add more rows if needed |  | Provide document code and version | Report here the reason of the change from previous version
Acceptance Criteria
Have all expected and planned task/deliverables been successfully completed? |  |  |  | YES/NO
Are all bugs with HIGH severity due to Safety YES Closed? (if any)* |  |  |  | YES/NO
Are all bugs with HIGH severity due to impact on basic feature that gets product unusable closed? (if any) |  |  |  | YES/NO
Are all bugs with HIGH severity due to impact on Performance Claim closed? (if any) |  |  |  | YES/NO
Are all bugs with HIGH severity due to safety risk with impact on Mitigation Method closed? (if any)* |  |  |  | YES/NO
Are all bugs with HIGH severity due to security risk defined as Uncontrolled closed? (if any)* |  |  |  | YES/NO
Are all bugs with HIGH severity due to vulnerability severity (refer to CVSS v.3 Score – Inpeco use) as Critical closed? (if any)" |  |  |  | YES/NO
Are all bugs with HIGH severity due to security risk with impact on loss of confidentiality closed? (if any) |  |  |  | YES/NO
Are all risks final risk levels acceptable (i.e. Medium/Low)? (refer to Final Risk Evaluation)* |  |  |  | YES/NO
Update the "Action Item Status" in the Action Item Sheet: Are all the action items closed? (if any) |  |  |  | YES/NO
Deployment Review Passed? |  |  |  | YES/NO
If one or more Acceptance Criteria answer is/are "NO", provide a justification to proceed with successfull Project closure in the Meeting Minutes section. (*) if the Acceptance Criteria answer is "NO", the Medical Affairs additional signature is required
Meeting Minutes
Report here the meeting minutes of the conducted review. For the Action Item, refer to "Action Items" sheet. Any additional notes/comments.

## Release to Market Review
Release to Market Review Meeting
Date | YYYY/MM/DD
Meeting Attendees and Roles
Name & Surname |  | Company Roles
Report the name and surname of the Independent Reviewer. (Contact the Head of Lifecycle unit or Q&R for the independent reviewer person) |  | Company Role - Independent Reviewer
Deliverable Check
Name |  | File | Note
Technical Service Bulleting/Instrument Service Advisory (TSB/ISA) [Document created] |  | Provide document code and version | Report here any reason of not applicability or not updated
Technical Data Sheet [Document updated] |  | Provide document code and version | Report here any reason of not applicability or not updated
Product Information [Document updated] |  | Provide document code and version | Report here any reason of not applicability or not updated
any other additional deliverable [Document signed] |  | Provide document code and version | Report here any reason of not applicability or not updated
Acceptance Criteria
Have all the expected registration/listing been completed? |  |  |  | YES/NO
Conclusion of the Design Transfer: are the design and development outputs verified as suitable for manufacturing? |  |  |  | YES/NO
Have all the expected content (e.g. packages, marketing documents, manuals) been shared? |  |  |  | YES/NO
Have the needed training to Distributors been planned? |  |  |  | YES/NO
Have all the Action Item been closed? |  |  |  | YES/NO
Release to Market Review Passed? |  |  |  | YES/NO
If one or more Acceptance Criteria answer is/are "NO", provide a justification to proceed with successfull Project closure in the Meeting Minutes section.
Meeting Minutes
Report here the meeting minutes of the conducted review. No Action Item shall remain open. Any additional notes/comments.
CUT IN identified | Report here the system (e.g. FLX.XXXX) - indicate it for all the Procuct Line

## Action Items
Action items
# | Open Date | Design Review | Description | Owner | Status | Notes/Updates | Due date | Justification
Action item ID | Date the Action Item has been opened. | Name of the review in which the Action Item has been opened | Description of the Action Item | Person in charge of closing the Action Item. | Open/Closed | Notes/Updates | Date of expected Action Item closure (Mandatory) | Justification for proceeding with Project closure while the Action Item remains open. (This Mandatory field should also include any constraints related to Action Item acceptance - e.g. No shipment planned before due date).

## Input for Excel (hidden)
STATUS | To be evaluated
Required - To be done
Completed
Not required
No Impact
QUESTIONS | YES | YES
| NO | YES WITH ACTION ITEM/S
| N/A | NO
REVIEW | Kick-off
Planning
Execution
Deployment
Previous Increment
STATUS | Open
On Going
Closed